## BH Petitioner CARE Plan
CARE Court Process Overview (BH Petitioner and CARE Plan)
Hearing # | CARE Process Outline Dates | Calendar Date | Counting Days | Day of the Week | Timeline Notes | CCP 1005 time (court days)
| Petition Filed | 2024-12-02 | 0 | Monday
| Court Prima Facie Review (if not met dismiss, if met continue, or possibly order augmentation report for more info) | 2024-12-03 | 1 | Tuesday | Reasonable time (assumed 1 court day) WIC 5977(a)(1) and (a)(3)(iii) [Report to Augment Petition]) | 1
| Personal Service on Respondent of Petition, Notice of Initial Hearing, and Order for Report (if ordered) | 2024-12-10 | 8 | Tuesday | No specific deadline for service provided in CARE Act or Rules, CRC 7.2235(a) just says that service shall be "before engaging Respondent and preparing a report". Section 5977(a)(3)(B) indicates BH serves Petitioner and Respondent that a report has been ordered and CRC 7.2235(a)(4) provides that the County shall serve a copy of the order and include a copy of the "petition packet filed to begin the proceedings." For timeline, assumed 5 court days to complete service since report is due within 14 court days. | 5
| BH Report Due (if ordered) | 2024-12-23 | 21 | Monday | Within 14 Court days from Court from Prima Facie Finding (WIC 5977(a)(3)(A)(i) | 14
| Personal Service of Report (if ordered) |  |  |  | CRC, Rule 7.2235(b)(3) requires that the report must be served on Respondent at least 5 court days before the hearing, but the Report itself is not due until the day of the Initial Hearing
1 | Initial Hearing | 2024-12-23 | 21 | Monday | Within 14 Court days from Court order from Prima Facie Finding | 14
| Personal Service on Respondent | 2024-12-24 | 22 | Tuesday | at least 5 court days before Initial Hearing (CRC 7.2235(c)(1) | -5
2 | Hearing on Merits (evidentiary hearing) | 2025-01-02 | 31 | Thursday | Within 10 calendar days from Initial Hearing (WIC 5977(b)(7)(A))
THIS IS WHERE THE PROCESS PICKS UP FROM NON-BEHAVIORAL HEALTH PETITIONER PROCESS
| Personal Service on Respondent | 2025-01-09 | 38 | Thursday | at least 5 court days before Subsequent Hearing (CRC 7.2235(c)(1) | -5
3 | Case Management Hearing (Status on Agreement or Set for CARE Plan Hearing) | 2025-01-16 | 45 | Thursday | Within 14 calendar days of Merits Hearing (5977(c)(2))
| Personal Service on Respondent | 2025-01-23 | 52 | Thursday | at least 5 court days before Subsequent Hearing (CRC 7.2235(c)(1) | -5
3.5 | Optional Continuance of Case Management Hearing to Develop CARE Agreement | 2025-01-30 | 59 | Thursday | 14 calendar days upon stipulation of parties (WIC 5977.1(a)(2)(B))
THIS IS WHERE THE CARE PLAN PROCESS DEVIATES FROM CARE AGREEMENT PROCESS
| Clinical Evaluation Report Due | 2025-02-15 | 75 | Saturday | No later than 5 calendar days before Clinical Evaluation Hearing
| Personal Service on Respondent | 2025-02-11 | 71 | Tuesday | at least 5 court days before Subsequent Hearing (CRC 7.2235(c)(1) | -5
4 | Clincial Evaluation Hearing (evidentiary hearing) | 2025-02-20 | 80 | Thursday | 21 calendar days from Case Management Hearing (WIC 5977.1(c)(1).)
| Personal Service on Respondent | 2025-02-27 | 87 | Thursday | at least 5 court days before Subsequent Hearing (CRC 7.2235(c)(1) | -5
4.5 | Optional Continuance to Complete Clinical Evaluation | 2025-03-06 | 94 | Thursday | maximum of 14 calendar days upon stipulation of parties (WIC 5977.1(a)(2)(B))
| CARE Plan due | 2025-03-20 | 108 | Thursday | 14 calendar days from Clinical Evaluation Hearing (WIC 5977.1(c)(3)(A))
| Personal Service on Respondent | 2025-03-13 | 101 | Thursday | at least 5 court days before Subsequent Hearing (CRC 7.2235(c)(1) | -5
5 | CARE Plan Review Hearing | 2025-03-20 | 108 | Thursday | 14 calendar days from the order to develop CARE Plan (WIC 5977.1(c)(6))
| Personal Service on Respondent | 2025-03-26 | 114 | Wednesday | at least 5 court days before Subsequent Hearing (CRC 7.2235(c)(1) | -5
5.5 | Optional Continuance for Supplemental Report re CARE Plan | 2025-04-03 | 122 | Thursday | no more than 14 calendar days (WIC 5977.1(d)(5) and (d)(6)
| BH Status Report Due | 2025-05-23 | 172 | Friday | no fewer than 5 court days prior to review hearing | -5
| Personal Service on Respondent | 2025-05-23 | 172 | Friday | at least 5 court days before Subsequent Hearing (CRC 7.2235(c)(1) | -5
6 | Status Review Hearing (CARE Plan) or Progress Hearing (CARE Agreement) | 2025-06-02 | 182 | Monday | no less frequently than every 60 calendar days after CARE plan (WIC 5977.2(a)(1) or 60 calendar days from approval of CARE Agreement (WIC 5977.1(a)(2)(A))
| BH Status Report Due | 2025-07-25 | 235 | Friday | no fewer than 5 court days prior to review hearing | -5
| Personal Service on Respondent | 2025-07-25 | 235 | Friday | at least 5 court days before Subsequent Hearing (CRC 7.2235(c)(1) | -5
7 | Status Review Hearing (CARE Plan) or Progress Hearing (CARE Agreement) | 2025-08-01 | 242 | Friday | no less frequently than every 60 calendar days after CARE plan (WIC 5977.2(a)(1) or 60 calendar days from approval of CARE Agreement (WIC 5977.1(a)(2)(A))
| BH Status Report Due | 2025-09-22 | 294 | Monday | no fewer than 5 court days prior to review hearing | -5
| Personal Service on Respondent | 2025-09-22 | 294 | Monday | at least 5 court days before Subsequent Hearing (CRC 7.2235(c)(1) | -5
8 | Status Review Hearing (CARE Plan) or Progress Hearing (CARE Agreement) | 2025-09-30 | 302 | Tuesday | no less frequently than every 60 calendar days after CARE plan (WIC 5977.2(a)(1) or 60 calendar days from approval of CARE Agreement (WIC 5977.1(a)(2)(A))
| BH Status Report Due | 2025-11-20 | 353 | Thursday | no fewer than 5 court days prior to review hearing | -5
| Personal Service on Respondent | 2025-11-20 | 353 | Thursday | at least 5 court days before Subsequent Hearing (CRC 7.2235(c)(1) | -5
9 | Status Review Hearing (CARE Plan) or Progress Hearing (CARE Agreement) | 2025-11-29 | 362 | Saturday | no less frequently than every 60 calendar days after CARE plan (WIC 5977.2(a)(1) or 60 calendar days from approval of CARE Agreement (WIC 5977.1(a)(2)(A))
| BH Status Report Due | 2026-01-21 | 415 | Wednesday | no fewer than 5 court days prior to review hearing | -5
| Personal Service on Respondent | 2026-01-21 | 415 | Wednesday | at least 5 court days before Subsequent Hearing (CRC 7.2235(c)(1) | -5
10 | Status Review Hearing (CARE Plan) or Progress Hearing (CARE Agreement) | 2026-01-28 | 422 | Wednesday | no less frequently than every 60 calendar days after CARE plan (WIC 5977.2(a)(1) or 60 calendar days from approval of CARE Agreement (WIC 5977.1(a)(2)(A))
| BH Status Report (with Final Assessment) Due | 2026-03-09 | 462 | Monday | Not fewer than 5 court days before One Year Status Hearing (11th month) (WIC 5977.3(a)(1)) | -5
| Personal Service on Respondent | 2026-03-09 | 462 | Monday | at least 5 court days before Subsequent Hearing (CRC 7.2235(c)(1) | -5
11 | One-Year Status Hearing (at 11th month) - Evidentiary Hearing, decide to continue or graduate or continue for another year | 2026-03-14 | 467 | Saturday | "In the 11th month of the process timeline" (WIC 5977.3(a)(1)) (interpreted to mean 11th month from adoption of CARE Plan, not filing of petition, though statute is not clear what "process timeline" means, but this interpretation made more sense with the "12th month after adoption of CARE Plan" reference in 5977.3(a)(3)(A)
| Graduation Plan (Agreement) Due | 2026-03-26 | 479 | Thursday | WIC 5977.3(a)(3) does not state when due, so made it 5 court days like most other reports | -5
| Personal Service on Respondent | 2026-03-26 | 479 | Thursday | at least 5 court days before Subsequent Hearing (CRC 7.2235(c)(1) | -5
12 | Graduation Hearing (12th Month) | 2026-04-03 | 487 | Friday | 12th Month after adoption of the CARE Plan (WIC 5977.3(a)(3)(A))
| BH Status Report Due | 2026-05-06 | 520 | Wednesday | no fewer than 5 court days prior to review hearing | -5
| Personal Service on Respondent | 2026-05-06 | 520 | Wednesday | at least 5 court days before Subsequent Hearing (CRC 7.2235(c)(1) | -5
12 | IF STAYING FOR ANOTHER YEAR, skip Graduation Hearing and continue 60 day status hearings: Status Review Hearing (CARE Plan) or Progress Hearing (CARE Agreement) | 2026-05-13 | 527 | Wednesday | no less frequently than every 60 calendar days after CARE plan (WIC 5977.2(a)(1) or 60 calendar days from approval of CARE Agreement (WIC 5977.1(a)(2)(A))
| BH Status Report Due | 2026-06-26 | 571 | Friday | no fewer than 5 court days prior to review hearing | -5
| Personal Service on Respondent | 2026-06-26 | 571 | Friday | at least 5 court days before Subsequent Hearing (CRC 7.2235(c)(1) | -5
13 | Status Review Hearing (CARE Plan) or Progress Hearing (CARE Agreement) | 2026-07-05 | 580 | Sunday | no less frequently than every 60 calendar days after CARE plan (WIC 5977.2(a)(1) or 60 calendar days from approval of CARE Agreement (WIC 5977.1(a)(2)(A))
| BH Status Report Due | 2026-08-18 | 624 | Tuesday | no fewer than 5 court days prior to review hearing | -5
| Personal Service on Respondent | 2026-08-18 | 624 | Tuesday | at least 5 court days before Subsequent Hearing (CRC 7.2235(c)(1) | -5
14 | Status Review Hearing (CARE Plan) or Progress Hearing (CARE Agreement) | 2026-08-25 | 631 | Tuesday | no less frequently than every 60 calendar days after CARE plan (WIC 5977.2(a)(1) or 60 calendar days from approval of CARE Agreement (WIC 5977.1(a)(2)(A))
| BH Status Report Due | 2026-10-12 | 679 | Monday | no fewer than 5 court days prior to review hearing | -5
| Personal Service on Respondent | 2026-10-12 | 679 | Monday | at least 5 court days before Subsequent Hearing (CRC 7.2235(c)(1) | -5
15 | Status Review Hearing (CARE Plan) or Progress Hearing (CARE Agreement) | 2026-10-17 | 684 | Saturday | no less frequently than every 60 calendar days after CARE plan (WIC 5977.2(a)(1) or 60 calendar days from approval of CARE Agreement (WIC 5977.1(a)(2)(A))
| BH Status Report Due | 2026-12-04 | 732 | Friday | no fewer than 5 court days prior to review hearing | -5
| Personal Service on Respondent | 2026-12-04 | 732 | Friday | at least 5 court days before Subsequent Hearing (CRC 7.2235(c)(1) | -5
16 | Status Review Hearing (CARE Plan) or Progress Hearing (CARE Agreement) | 2026-12-11 | 739 | Friday | no less frequently than every 60 calendar days after CARE plan (WIC 5977.2(a)(1) or 60 calendar days from approval of CARE Agreement (WIC 5977.1(a)(2)(A))
| BH Status Report Due | 2027-01-26 | 785 | Tuesday | no fewer than 5 court days prior to review hearing | -5
| Personal Service on Respondent | 2027-01-26 | 785 | Tuesday | at least 5 court days before Subsequent Hearing (CRC 7.2235(c)(1) | -5
17 | Status Review Hearing (CARE Plan) or Progress Hearing (CARE Agreement) | 2027-02-02 | 792 | Tuesday | no less frequently than every 60 calendar days after CARE plan (WIC 5977.2(a)(1) or 60 calendar days from approval of CARE Agreement (WIC 5977.1(a)(2)(A))
| Graduation Plan (Agreement) Due | 2027-03-08 | 826 | Monday | WIC 5977.3(a)(3) does not state when due, so made it 5 court days like most other reports | -5
| Personal Service on Respondent | 2027-03-08 | 826 | Monday | at least 5 court days before Subsequent Hearing (CRC 7.2235(c)(1) | -5
18 | Graduation Hearing (12th Month) | 2027-03-14 | 832 | Sunday | 12th Month after adoption of the CARE Plan (WIC 5977.3(a)(3)(A))
Formulas:
Calendar Date = WORKDAY([Calendar Date, row above],[CCP 1005 time (court days)],Holidays!A:A)
Calendar Date = WORKDAY(C4,[CCP 1005 time (court days)],Holidays!A:A)

## BH Petitioner CARE Agreement
CARE Court Process Overview (BH Petitioner and CARE Agreement)
Hearing # | CARE Process Outline Dates | Calendar Date | Counting Days | Day of the Week | Timeline Notes | CCP 1005 time (court days)
| Petition Filed | 2024-12-02 | 0 | Monday
| Court Prima Facie Review (if not met dismiss, if met continue, or possibly order augmentation report for more info) | 2024-12-03 | 1 | Tuesday | Reasonable time (assumed 1 court day) WIC 5977(a)(1) and (a)(3)(iii) [Report to Augment Petition]) | 1
| Personal Service on Respondent of Notice of Initial Hearing, "Petition packet", and Order for Report (if ordered) | 2024-12-16 | 14 | Monday | at least 5 court days before Initial Hearing (CRC 7.2235(b)(1)) | -5
| BH Report Due (if ordered) | 2024-12-23 | 21 | Monday | Within 14 Court days from Court from Prima Facie Finding (WIC 5977(a)(3)(A)(i) | 14
| Personal Service of Report (if ordered) |  |  |  | CRC, Rule 7.2235(b)(3) requires that the report must be served on Respondent at least 5 court days before the hearing, but the Report itself is not due until the day of the Initial Hearing
1 | Initial Hearing | 2024-12-23 | 21 | Monday | Within 14 Court days from Court order from Prima Facie Finding | 14
| Personal Service on Respondent | 2024-12-24 | 22 | Tuesday | at least 5 court days before Initial Hearing (CRC 7.2235(c)(1) | -5
2 | Hearing on Merits (evidentiary hearing) | 2025-01-02 | 31 | Thursday | Within 10 calendar days from Initial Hearing (WIC 5977(b)(7)(A))
THIS IS WHERE THE PROCESS PICKS UP FROM NON-BEHAVIORAL HEALTH PETITIONER PROCESS
| Personal Service on Respondent | 2025-01-09 | 38 | Thursday | at least 5 court days before Subsequent Hearing (CRC 7.2235(c)(1) | -5
3 | Case Management Hearing (Status on Agreement or Set for CARE Plan Hearing) | 2025-01-16 | 45 | Thursday | Within 14 calendar days of Merits Hearing (5977(c)(2))
| Personal Service on Respondent | 2025-01-23 | 52 | Thursday | at least 5 court days before Subsequent Hearing (CRC 7.2235(c)(1) | -5
3.5 | Optional Continuance of Case Management Hearing to Develop CARE Agreement | 2025-01-30 | 59 | Thursday | 14 calendar days upon stipulation of parties (WIC 5977.1(a)(2)(B))
THIS IS WHERE THE CARE AGREEMENT PROCESS DEVIATES FROM CARE PLAN PROCESS
| BH Status Report Due | 2025-03-24 | 112 | Monday | no fewer than 5 court days prior to review hearing | -5
| Personal Service on Respondent | 2025-03-24 | 112 | Monday | at least 5 court days before Subsequent Hearing (CRC 7.2235(c)(1) | -5
4 | Progress Hearing (CARE Agreement) | 2025-03-31 | 119 | Monday | "set a progress hearing for 60 calendar days" from approval or modification of CARE Agreement (WIC 5977.1(a)(2)(A)) NOTE: code does not appear to have flexibility on the timing (i.e. it doesn't say "within 60 days") so we may need to interpret this to work for the court's calendar.
NOTE: The code is silent on what happens with a CARE Case once an Agreement is reached and the 60 day Progress Hearing is held. It doesn't say to hold additional hearings after the 60 day progress hearing, and the 11th month hearing and the graduation hearing appear to only apply to CARE Plans (not CARE Agreements).
NOTE: The CARE Act is silent on what will happen if the parties do not follow the CARE Agreement. Can a party demand a "clinical evaluation hearing" and start the CARE Plan process? The CARE Act language in WIC 5977.3(c) suggests that only Respondents on a CARE Plan can be "reappointed" to the CARE Process for 1 additional year.
NOTE: Team should consider what practice we would like to use to close CARE cases when an agreement is reached? Set a "Progress Hearing" at the 1 year mark to terminate court's jurisdiction? 1 year from what? Filing of Petition? Entering the CARE Agreement? The Progress Hearing?
Formulas:
Calendar Date = WORKDAY([Calendar Date, row above],[CCP 1005 time (court days)],Holidays!A:A)
Calendar Date = WORKDAY(C8,[CCP 1005 time (court days)],Holidays!A:A)

## NonBH Petitioner
CARE Court Process Overview (Non-BH Petitioner)
Hearing | CARE Process Outline Dates | Calendar Date | Counting Days | Day of the Week | Timeline Notes | CCP 1005 time (court days)
| Petition Filed | 2024-12-02 | 0 | Monday
| Court Prima Facie Review (if not met dismiss, if met order BH report) | 2024-12-03 | 1 | Tuesday | Reasonable time (assumed 1 court day) WIC 5977(a)(1); report is WIC 5977(a)(3)(B) | 1
| BH completes Personal Service of Order for BH Report and copy Petition Packet filed by Petitioner on Respondent; service of all documents on all other parties via mail/email | 2024-12-10 | 8 | Tuesday | No specific deadline for service provided in CARE Act or Rules, CRC 7.2235(a) just says that service shall be "before engaging Respondent and preparing a report". Section 5977(a)(3)(B) indicates BH serves Petitioner and Respondent that a report has been ordered and CRC 7.2235(a)(4) provides that the County shall serve a copy of the order and include a copy of the "petition packet filed to begin the proceedings." For timeline, assumed 5 court days to complete service since report is due within 14 court days. | 5
| BH Report Due (or Optional request for continuance to engage Respondent) | 2024-12-23 | 21 | Monday | Within 14 Court days from Court from order for Report/Prima Facie (WIC 5977(a)(3)(A)(iii) ; Continuance no more than 30 calendar days (WIC 5977(a)(4)) | 14
| Optional: Personal Service on Order for Continuance to Complete Report | 2024-12-28 | 26 | Saturday | Within 5 calendar days of order for continuance (CRC Rule 7.2235(a)(5)
| BH Report Due (on continuance) | 2025-01-22 | 51 | Wednesday | No more than 30 calendar days (WIC 5977(a)(4)) | 30
| Court Reviews Report and Dismisses or Sets Initial Appearance if Prima Facie shown within 14 court days | 2025-01-27 | 56 | Monday | Within 5 calendar days of receipt of BH Report (WIC5977(a)(5))
| BH completes Personal Service of Notice of Hearing/Report on Respondent | 2025-02-07 | 67 | Friday | at least 5 court days before Initial Hearing (CRC 7.2235(b)(1) | -5
1 | Initial Hearing | 2025-02-18 | 78 | Tuesday | Within 14 Court days from Court order from Review of BH Report (WIC 5977(a)(5)(C)(i).) | 14
| Personal Service on Respondent | 2025-02-21 | 81 | Friday | at least 5 court days before Initial Hearing (CRC 7.2235(b)(1) | -5
2 | Hearing on Merits (evidentiary hearing) and substitute BH as petitioner | 2025-02-28 | 88 | Friday | Within 10 calendar days from Initial Hearing (or optional Continuance of Intital Hearing) (WIC 5977(b)(7)(A))
NOTE: All subsequent steps follow the process for BH Petitioner for a CARE Agreement or CARE Plan following the Hearing on the Merits
Formulas:
Calendar Date = WORKDAY([Calendar Date, row above],[CCP 1005 time (court days)],Holidays!A:A)
Calendar Date = WORKDAY(C4,[CCP 1005 time (court days)],Holidays!A:A)

## Holidays
2024-01-01 | New Year's Day
2024-01-15 | Martin Luther King, Jr. Birthday
2024-02-12 | Lincoln Day
2024-02-19 | Presidents' Day
2024-04-01 | Cesar Chavez Day
2024-05-27 | Memorial Day
2024-06-19 | Juneteenth
2024-07-04 | Independence Day
2024-09-02 | Labor Day
2024-09-27 | Native American Day
2024-11-11 | Veterans Day
2024-11-28 | Thanksgiving Day
2024-11-29 | Day after Thanksgiving
2024-12-25 | Christmas Day
2025-01-01 | New Year's Day
2025-01-20 | Martin Luther King, Jr. Birthday
2025-02-12 | Lincoln Day
2025-02-17 | Presidents' Day
2025-03-31 | Cesar Chavez Day
2025-05-26 | Memorial Day
2025-06-19 | Juneteenth
2025-07-04 | Independence Day
2025-09-01 | Labor Day
2025-09-26 | Native American Day
2025-11-11 | Veterans Day
2025-11-27 | Thanksgiving Day
2025-11-28 | Day after Thanksgiving
2025-12-25 | Christmas Day
2026-01-01 | New Year's Day
2026-01-19 | Martin Luther King, Jr. Birthday
2026-02-12 | Lincoln Day
2026-02-16 | Presidents' Day
2026-03-31 | Cesar Chavez Day
2026-05-25 | Memorial Day
2026-06-19 | Juneteenth
2026-07-03 | Independence Day
2026-09-07 | Labor Day
2026-09-25 | Columbus Day
2026-11-11 | Veterans Day
2026-11-26 | Thanksgiving Day
2026-11-27 | Day after Thanksgiving
2026-12-25 | Christmas Day